## Sheet1
Issues | Estimated time length(hours) | Actual time length (hours) | Day of the Sprint | Target | Actual
Low fidelity prototype | 2 | 3 | 2 | 11.63 | 14.5
High fidelity prototype | 3 | 3.5 | 4 | 10.26 | 14.5
User Class diagram | 2 | 0.5 | 6 | 8.89 | 10.5
Reviews Class diagram | 1.5 | 2 | 10 | 7.52 | 8.5
Activity Diagram | 2 | 1.5 | 12 | 6.15 | 5
Owner Class Diagram | 1 | 1 | 14 | 4.78 | 2
Job Class Diagram | 1 | 2 | 16 | 3.41 | 2
Create Story points and burndown chart | 1 | 1 | 18 | 1.94 | 1
| 13.5 | 14.5 | 20 | 0 | 0