## Sheet1
Issues | Estimated time length(hours) | Actual time length (hours) | Day of the Sprint | Target | Actual
User Module | 2 | 1 | 3 | 44.11 | 45.5 | 1.13
Customer module | 1 | 1 | 5 | 41.85 | 44.5
Reviews module | 1 | 1 | 7 | 39.59 | 39.5
Job module | 2 | 2 | 10 | 36.2 | 37.5
Worker module | 1 | 1 | 12 | 33.94 | 29.5
Create Worker Dashboard | 1 | 1 | 14 | 31.68 | 29.5
Create Customer Dashboard | 1 | 1 | 17 | 28.29 | 29.5
Create Jobs Display page | 1 | 1 | 19 | 26.03 | 29.5
Create user review page | 1 | 1 | 21 | 23.77 | 29.5
Create Owner add job page | 1 | 1 | 24 | 20.38 | 23.5
Finish Jobs Display page | 3 | 3 | 26 | 18.12 | 23.5
Finish user review page | 4 | 6 | 28 | 15.86 | 22.5
Finish owner add job page | 2 |  | 31 | 12.47 | 18.5
Finish Worker Dashboard | 2 | 6 | 33 | 10.21 | 13.5
Finish Customer Dashboard | 2 | 6 | 35 | 7.95 | 10.5
Account Page | 2 | 2 | 38 | 4.56 | 3.5
Login System | 2 | 2 | 40 | 2.3 | 3.5
Login Page | 2 | 2 | 42 | 0 | 0
User Information Page | 2 | 2
Burndown Chart | 1 | 1
Standups | 1 | 1
Divide Issues further | 2 | 1
Create admin user | 1
Deep dive review django | 2 | 2
Pretty up Jobs Display page | 1.5 | 1.5
Pretty up user Review page | 1.5 | 1.5
Pretty up owner add job pg | 1.5
Pretty up Worker Dashboard | 1.5 | 1.5
Pretty up Customer Dashboard | 1.5 | 1.5
| 47.5 | 51